## Sheet1
CHATHAM COUNTY SANITARY SEWER SYSTEM
CAPITAL IMPROVEMENT PLAN
Rev. May 2018
PROJECT | DESCRIPTION | YR 1 | YR 2 | YR 3 | YR 4 | YR 5 | Beyond
Causton Bluff Lift Station | rehab lift station and install bypass pump | [5 empty] | 75000
Central Avenue Lift Station | replace current generator w/bypass pump | 80000
Engineering Services | design, prepare bid packages & monitor const | 50000 |  | 50000 |  | 50000
Galebreak Lift Station | rehab lift station and install bypass pump |  |  | 45000 | 175000
Hopecrest Lift Station | rehab lift station and install bypass pump |  | 45000 | 225000
Sallie Mood Dr Force Main | replace line | 100000 | 1000000
Central Ave Force Main | replace line |  |  | 100000 | 1000000
Line rehab | slip line force mains | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
Manhole rehab | replace or line manholes | 75000 | 75000 | 75000 | 75000 | 75000 | 200000
Nancy Place Lift Station | rehab lift station and install bypass pump |  |  |  | 50000 | 200000
Runaway Point Lift Station | upgrade equipment | [5 empty] | 75000
Salcedo Lift Station | rehab lift station, install bypass pump and new fence |  |  | 45000 | 190000
Sheftall Bluff Lift Station | rehab lift station and install bypass pump | 400000
Winterberry Lift Station | upgrade equipment | [5 empty] | 75000
Wylly Island Lift Station | rehab lift station and install bypass pump | 250000 |  | 180000
|  | 1055000 | 1220000 | 820000 | 1590000 | 425000 | 5110000